## Review progress
# | Review point | Status | Writing only? | What's left
Reviewer 1
1 | Own edit on wrong image not counted as error | Done | No | —
2 | Partner edit on matching image wrongly counted as error | Done | No | —
3 | Swap-accuracy direction conflicted with safety goal | Measured; no win yet | No | Improve answer-level (cut stale answers on swap); then we can claim it
4 | Components not isolated (vision / text / LiveEdit / fusion) | Done | No | —
5 | Binary false-activation may overstate baseline leak | Done | No | —
6 | Only 100 edits; pool size untested | Partly done | No | Optional: more edit orders + Easy-VQA pool-size curve
7 | Repeated prompts / visual collisions may explain residual | Partly done | No | Optional: hard-neg difficulty strata + small human check of pairs
8 | Only one backbone and one editor | In progress | No | Finish LLaVA Dual-Expert Keys train + eval; then other editors
9 | Residual leak still high | Measured; no win yet | No | Method retry to cut absolute hard-neg leak under honest pools
Reviewer 2
1 | CARML / MSCKE not compared | Partly done | No | MSCKE public-code check + related-work write-up
2 | Leak metric may be LiveEdit-specific | Not started | No | Run same leak protocol on other editors
3 | Only author-built baseline | Done | No | —
4 | No gain on Rel / Gen / Loc | Partly done | Yes | Write paper section / plot leading with leak vs reliability
5 | Single BLIP-2 backbone | In progress | No | Finish LLaVA Dual-Expert Keys train + eval (due 15 Oct)
AI reviewer
1 | Conflicting targets (FPR / Swap / equation) | Partly done | No | Answer-level still weak; do not claim swap-answer rescue until fixed
2 | Missing always-reject / routing controls | Partly done | Yes | Paper polish: present controls clearly in tables/text
3 | Novelty vs LiveEdit / CARML unclear | Partly done | Yes | Write side-by-side routing-spec table in the paper
4 | No Dual-Expert Keys without adversarial training; no vision/text-only | Done | No | —
5 | Lifelong scaling claimed but not tested | Done | No | —
6 | Prototype score underspecified | Not started | Yes | Write concrete prototype-score definition in method section
7 | Hard-negative difficulty strata + human check | Later | No | Optional later if time remains
8 | Explain VLKEB vs Easy-VQA residual gap | Done | No | —
9 | Multi-seed reuses same checkpoints | Not started | No | Run five evaluation seeds (and training seeds if time)
10 | Hard-negative missing from VLKEB main tables | Done | No | —
11 | Writing nits (terms, spelling, hyperparameters) | Partly done | Yes | Clean draft: spelling, terms, figure seed labels, report hyperparameters
Writing only? Yes = paper/writing only. What's left = remaining work (— if nothing left).